## Project Portfolio Dashboard
PROJECT PORTFOLIO DASHBOARD
DELIVERY TIMELINE & RESOURCES
PROJECT FINANCIALS | RISK ANALYSIS
OPEN & PENDING ACTIONS

## Data
PROJECT PORTFOLIO DATA
PROJECT NAME | TIMELINE |  |  |  | NUMBER OF TEAM MEMBERS | BUDGET |  |  | RISKS |  |  | OPEN |  | PENDING ACTIONS
| CALENDAR | BEGIN | FINISH | # of DAYS |  | PROJECTED | ACTUAL | REMAINDER | HIGH | MEDIUM | LOW | ISSUES | REVISIONS
ProjectA | 2016-01-01 | 2016-02-22 | 2016-06-11 | 110 | 6 | 383279 | 457923 | -74644 | 0 | 6 | 7 | 1 | 3 | 3
ProjectB | 2016-02-01 | 2016-02-12 | 2016-10-22 | 253 | 9 | 487736 | 283548 | 204188 | 4 | 3 | 5 | 0 | 0 | 3
ProjectC | 2016-03-01 | 2016-04-20 | 2016-11-17 | 211 | 7 | 104275 | 322727 | -218452 | 1 | 2 | 3 | 3 | 3 | 1
ProjectD | 2016-04-01 | 2016-05-10 | 2016-09-15 | 128 | 7 | 143554 | 440184 | -296630 | 2 | 4 | 7 | 1 | 2 | 2
ProjectE | 2016-05-01 | 2016-05-12 | 2016-10-29 | 170 | 10 | 126508 | 522875 | -396367 | 1 | 2 | 0 | 3 | 3 | 3
ProjectF | 2016-06-01 | 2016-07-29 | 2017-03-10 | 224 | 7 | 67092 | 329792 | -262700 | 4 | 6 | 7 | 0 | 1 | 4
ProjectG | 2016-07-01 | 2016-07-20 | 2017-02-06 | 201 | 9 | 401508 | 27945 | 373563 | 4 | 4 | 1 | 2 | 1 | 4
ProjectH | 2016-08-01 | 2016-08-17 | 2017-01-15 | 151 | 11 | 170871 | 227513 | -56642 | 4 | 0 | 7 | 2 | 1 | 0
ProjectI | 2016-09-01 | 2016-09-29 | 2017-02-23 | 147 | 6 | 126336 | 407375 | -281039 | 3 | 5 | 4 | 0 | 0 | 1
ProjectJ | 2016-10-01 | 2016-11-02 | 2016-12-28 | 56 | 11 | 309989 | 69245 | 240744 | 0 | 3 | 3 | 0 | 0 | 2
ProjectK | 2016-11-01 | 2017-01-02 | 2017-04-13 | 101 | 5 | 258679 | 279129 | -20450 | 4 | 2 | 6 | 2 | 2 | 3
ProjectL | 2016-12-01 | 2016-12-31 | 2017-05-11 | 131 | 8 | 279463 | 340993 | -61530 | 2 | 5 | 3 | 2 | 3 | 0
ProjectM | 2017-01-01 | 2017-03-09 | 2017-07-05 | 118 | 11 | 281985 | 567108 | -285123 | 1 | 6 | 7 | 1 | 0 | 2
ProjectN | 2017-02-01 | 2017-04-09 | 2020-02-12 | 1039 | 11 | 474106 | 272201 | 201905 | 2 | 5 | 3 | 2 | 2 | 1
ProjectO | 2017-03-01 | 2017-04-26 | 2017-12-26 | 244 | 9 | 202538 | 213031 | -10493 | 4 | 7 | 1 | 2 | 0 | 2
ProjectP | 2017-04-01 | 2017-05-06 | 2017-10-06 | 153 | 10 | 309256 | 325869 | -16613 | 0 | 5 | 3 | 1 | 0 | 2